## Isabel
Timesheet for Isabel Loney - Change sheets at the bottom!
Date | Task Description | Estimated (Hours) | Reasoning for estimate | Actual(Hours)
2024-09-05 | Team Meeting | 0.5 | Overview meeting - scheduled 12:30-1 | 0.5
2024-09-10 | Team Meeting | 1 | Work distribution meeting - 1 hour max planned | 0.5
2024-09-11 | Programming: Player.py functions | 2 | Intuition based on workload and complexity | 1.25
2024-09-12 | GTA meeting | 0.25 | Scheduled for 12:15-12:30 | 0.167
2024-09-15 | Testing, commenting, and clean up | 3 | A few days away from code; may need extra time to get caught up | 1
Total |  | 6.75 |  | 3.417
2024-09-18 | Team Meeting | 0.5 | Usually the amount of time team meetings take | 0.5
2024-09-19 | GTA Meeting | 0.25 | Scheduled for 12:15-12:30 | 0.25
2024-09-25 | SFX Programming | 2 | Intuition based on workload and complexity | 1.5
2024-09-26 | GTA Meeting | 0.25 | Scheduled for 12:15-12:30 | 0.1
2024-09-28 | Final documentation | 0.5 |  | 0.25
|  | 3.5 |  | 2.6

## Ginny
Timesheet for Ginny Ke - Change sheets at the bottom!
Date | Task Description | Estimated (Hours) | Reasoning | Actual(Hours)
2024-09-05 | Team Meeting | 0.5 | 1st brief team meeting for introductions and programming language decision | 0.5
2024-09-10 | Programming: draft functions in board.py | 1 | simple function implementation, shouldn't take longer than an hour depending on how other functions are created | 1
2024-09-10 | Team Meeting | 1 | 2nd team meeting to decide how to divvy the project up | 0.5
2024-09-12 | GTA Meeting | 0.25 | Brief intro meeting with the GTA to discuss progress. | 0.167
2024-09-15 | Programming: Comment code and add header in board.py | 0.25 | add comments to each approximately 15 lines of code | 0.25
2024-09-15 | Programming: Clean up comments and add prologue | 0.5 | add header and prologue to board.py, using a previous header template so it shouldn't take too long | 0.25
Total |  | 3.5 |  | 2.667
Project 2
2024-09-18 | Team Meeting | 0.5 | Went over requirements and tasks for each person | 0.5
2024-09-19 | GTA Meeting | 0.15 | Demo, discussion of Project 2 | 0.25
2024-09-26 | GTA Meeting | 0.15 | Discussion of inherited project 2 code | 0.1
2024-09-27 | Programming: implement randomPlaceShips for AI ship placement. Places ship randomly on board | 0.25 | Have to look at inherited code to see where function should go | 0.61
2024-09-28 | programming: add user menu | 1 | It was really difficult to sift through all 1000 lines of code to find where i could implement the user menu | 1.5
2024-09-29 | Programming/Testing: fix randomplaceship | 2 | Testing of the program and implementing randomplaceship function | 3.5
2024-09-29 | Documentation File | 0.25 | Create documentation file, didn't take too long as we have a template | 0.2
Total |  | 4.3 |  | 6.66

## Dylan
Timesheet for Dylan Sailors - Change sheets at the bottom!
Date | Task Description | Estimated | Estimate Reason | Actual
2024-09-05 | team meeting | 0.5 | This is the planned time that we allotted to get the meeting done. | 0.5
2024-09-10 | team meeting to split tasks | 1 | We plan for it to take an hour in hopes to get a good plan going | 0.5
2024-09-12 | complete assigned functions in board.py | 2 | I feel like this shouldn't take me any more than 2 hours to complete | 2
2024-09-12 | GTA meeting | 0.25 | This is the time slotted time for the meeting | 0.167
2024-09-14 | assist in merging code and bug fixing | 1 | Should only take about an hour if all goes well + some wiggle room for errors | 2
2024-09-15 | finalize comments and changes before merging to the main branch | 1 | It's just minor fixes and adding comments to place_ship in the board.py file so nothing that takes up too much time | 0.5
Total |  | 5.75 |  | 5.667
Project 2
Date | Task Description | Estimated | Estimate Reason | Actual
2024-09-18 | Team meeting | 0.5 | assigned tasks and went over the project requirements | 0.5
2024-09-19 | GTA Meeting | 0.25 | This is the time slotted time for the meeting | 0.167
2024-09-26 | GTA meeting | 0.25 | This is the time slotted time for the meeting | 0.1
2024-09-28 | Code: aiMediumTurn() aiHardTurn() along with bug fixing and commenting | 3 | this one will take a while so im guessing this time in hopes that it won't take longer | 4
Total |  | 4 |  | 4.767

## Jackson
Timesheet for Jackson Wunderlich - Change sheets at the bottom!
Project 1
Date | Task Description | Estimated (hr) | Reason | Actual (hr)
2024-09-05 | Team Meeting | 0.5 | Short meeting for introductions, choosing language | 0.5
2024-09-10 | Team Meeting | 1 | Splitting tasks, may take a while to get things evenly balanced | 0.5
2024-09-12 | GTA Meeting | 0.25 | 15 minute meeting for introduction and workload explanation | 0.167
2024-09-15 | Bug fixes, branch merging, testing | 2 | Merging + time for bug fixes if there are more issues than expected | 2.5
Total |  | 3.75 |  | 3.667
Project 2
Date | Task Description | Estimated (hr) | Reason | Actual (hr)
2024-09-18 | Team Meeting | 0.5 | Choosing custom addition, dividing work | 0.5
2024-09-19 | GTA Meeting | 0.25 | Demo for project 1 | 0.25
2024-09-26 | GTA Meeting | 0.25 | Project 2 discussion | 0.25
2024-09-28 | Easy AI turn and AI integration | 2.5 | Most time will probably be spent on making AI work with the project | 4
Total |  | 3.5 |  | 5

## Anakha
Timesheet for Anakha Krishna - Change sheets at the bottom!
Project 1
Date | Task Description | Estimated (Hours) | Reason for Estimate | Actual(Hours)
2024-09-05 | Team Meeting | 0.5 | Initial team meeting for introductions and looking over rubric. Time limited due to class schedules | 0.5
2024-09-10 | Team Meeting | 1 | Team meeting for distributing work. Might be difficult to come to a consensus on how to split things and decide timeline for the project | 0.5
2024-09-10 | Create file templates for classes and methods | 1 | Writing class and method names and creating the files for the basic program structure of the project. Not a lot of actual coding, so should be quick | 1.5
2024-09-12 | create draft code for Game.py | 2 | Trying to figure out how to write it based on the code that was just written in Player.py might take some extra time | 1
2024-09-12 | GTA Meeting | 0.25 | Scheduled time for GTA meeting | 0.167
2024-09-15 | Commenting of game.py, main.py, ship.py and comment modifications to other files as needed | 1 | Mostly just source and easy inline comments. Just a lot to get through so might take an hour | 1
2024-09-15 | Code documentation, repo cleanup, final merging into main branch, assignment submission | 1 | Need to write up documentation, might have some issues with Git, have to do final check of all requirements | 1
Total |  | 6.75 |  | 5.667
Project 2
Date | Task Description | Estimated (Hours) | Reason for Estimate | Actual(Hours)
2024-09-18 | Team Meeting | 0.5 | Quickly go over rubric and basic requirements | 0.5
2024-09-18 | Create requirements list | 0.5 | Create requirements list Google Doc and template code for new features. Might take a while due to needing to plan the code structure | 1
2024-09-19 | GTA Meeting | 0.25 | Demo Project 1, go over project 2 | 0.25
2024-09-26 | GTA Meeting | 0.25 | Brief discussion of current project 2 progress | 0.15
2024-09-26 | Start AnimationManager code | 1 | Just going to work on adding the assets and getting class setup going | 1
2024-09-27 | Finish AnimationManager code | 2 | Might take a while to figure out pygame stuff | 2
2024-09-28 | Create documentation document, send final action items | 0.25 | Just going to send a quick message with final action items to get repo prepared for submission and create the documentation document | 0.5
2024-09-29 | Finish commenting, documentation, and peer eval | 1 | Pretty straightforward, not a lot of code to comment and document so should be fast | 1
Total |  | 5.75 |  | 6.4