## Sheet1
Log Number | Team Member | Date | Hours | Minutes | Description
1 | John Newman | 2024-09-10 | 0 | 15 | ship class basic structure
2 | John Newman | 2024-09-10 | 0 | 19 | creating estimated person hours list
3 | John Newman | 2024-09-10 | 0 | 3 | completing ship class constructor
4 | Landon Pyko | 2024-09-10 | 0 | 45 | started PyGame class and created toplevel file, as well as create the other .py files that we'll need
5 | Andrew McFerrin | 2024-09-10 | 1 | 0 | set up battleship class and started to work on its functions
6 | Aiden Patel | 2024-09-10 | 1 | 40 | changed formatting of PyGame class and started to create the first phase of the game which includes the ship number selection
7 | Aiden Patel | 2024-09-10 | 3 | 30 | created a large amount of the game loop logic and helper functions. Helpers include translating between coordinates and pixels as well as the bones for drawing ships and shots. Base shooting gameplay also implemented but still need to work on placing ships. Images also need to be created still since they are placeholder names as of right now.
8 | Landon Pyko | 2024-09-11 | 1 | 0 | made test.py to test specific pygame features. got rectangle object to move around properly on screen. still working on ship placement
9 | John Newman | 2024-09-11 | 0 | 6 | updated Ship class in ship.py to include numHits function which returns an int that is the number of times the ship has been hit. Also commented all functions in ship.py
10 | Aiden Patel, Andrew McFerrin, John Newman, Kai Achen, Landon Pyko | 2024-09-11 | 0 | 10 | GTA meeting and after meeting chat.
11 | Andrew McFerrin | 2024-09-11 | 0 | 40 | worked more on the Battleship methods
12 | Landon Pyko | 2024-09-11 | 1 | 30 | Got ship placement working properly in a separate file. Just need to add collision checking
13 | Aiden Patel | 2024-09-11 | 2 | 0 | Created Battleship background asset and ship assets (not pushed yet, will do in the morning when back on my PC)
14 | John Newman | 2024-09-12 | 0 | 3 | in Ship class create _size attribute and get_size function to return size of ship in case of debugging.
15 | Kai Achen | 2024-09-12 | 0 | 30 | Created board.py and added constructor and allSunk() methods
16 | Kai Achen | 2024-09-12 | 1 | 0 | created board.py shoot, wasShot, isSunk, setBoard, _placeShip methods and commented file
17 | Landon Pyko | 2024-09-12 | 1 | 30 | More work on board navigation and placing ships. Almost there. Need to work on alignment of ships with board and left placement acting wonky
18 | Andrew McFerrin | 2024-09-12 | 0 | 30 | added comments and updated turn logic
19 | John Newman | 2024-09-12 | 4 | 7 | Update test.py a lot Added comments to most of the code Created functions to check if ship goes off map or intersects another ship Added Ship class to check for intersections using actual coords and not pixels Commented out some unused code
20 | Aiden Patel | 2024-09-13 | 1 | 15 | updated board background to allow for row and column label space. Created assets to represent missed, hit, and sunk shots on the board
21 | Aiden Patel | 2024-09-13 | 0 | 45 | added labels to background asset and pushed it up along with the shot markers. Changed the coords to pix and pix to coords values in the file to match the updated background size
22 | Aiden Patel | 2024-09-13 | 0 | 30 | created welcome screen, passing screens, and win screen and pushed them up. (nothing too fancy but will at least be good for testing even if we want to change it later)
23 | John Newman | 2024-09-13 | 4 | 59 | Pygameloop: now has ship placement, accurate scaling, shot tracking, battleship creation Battleship: change take turn to be simpler, shoot at current board effectively, also call setboard on boards as that doesn't happen autmatically ship: create documentation thing at the top board: Fix a few erroneous usage of row instead of rowNum, changed setboard to work with ship coords instead of whatever it was prior, changed placeship to called directly on the coords instead of looping to find match. In summary: game runs to first turn with mostly accurate graphics(artifacts from ship creation still exist) and updated things around to facilitate that. Still need to implement shooting and number of ship selection. Also added temp textures for everything that was missing one. do not forget to replace them
24 | Aiden Patel | 2024-09-14 | 0 | 20 | Updated the images used, changed some logic to fix shot drawing. Issue with shooting rooted in Board that needs to be ironed out
25 | Aiden Patel, Andrew McFerrin, Landon Pyko | 2024-09-14 | 0 | 25 | meeting discussing shoot mechanics. Need to remove enumerate from shooting in the Board class to hopefully fix the issue with a list being passed in as a coordinate
26 | Landon Pyko | 2024-09-14 | 0 | 30 | Touched up some stuff and pinpointed the issue with winner detection (stemming from board.py’s shoot)
27 | Aiden Patel | 2024-09-14 | 1 | 15 | Cleaned Board and Battleship and removed unneeded functions. Choosing ships now works but stuck in white screen loop from passing screen that needs to be addressed. Pix to coords also not working since screen scaling has changed
28 | Andrew McFerrin | 2024-09-14 | 0 | 40 | Cleaned up some errors on battleship and removed an unnecessary method
29 | John Newman | 2024-09-14 | 0 | 15 | Fixed pixtoCoords to work with both boards based on turn pygameloop: changed pixtocoords function to track turn so the right board is targeted based on turn. Probably could add some kind of constant display of coords targeted to help debugging and gameplay board: ran into error with isSunk being called with too many arguments, isSunk on ship class is just a method on itself, nothing needs to be passed in.
30 | Landon Pyko | 2024-09-14 | 0 | 15 | Fixed up drawShips in pygame
31 | John Newman | 2024-09-14 | 0 | 44 | Polish game logic, update shot textures to be bigger *Shot.pngs: have been scaled up from 16 to 50 pixels. old version are left in case desired battleship.py: changed _curboard as its not the players board you want, but the enemies. board.py: updated the coords so ships now create occupied and unhit instead of unnocupied and missed flag pygameloop.py: Initiailized to welcome screen instead of ship placement before and after game loop. Commented out useless code at end, left reminded to trim more fat later PASSING SCREEN FIX, instead of ¦ used or as ¦ is bitwise or and apparently pg.keydown and mousebuttondown don't bitwise or nicely. In Summary, updated graphics, trimmed fat, fixed passingScreen error Game is mostly ready besides graphics artifacts and quality of life things.
32 | Aiden Patel | 2024-09-15 | 1 | 0 | Implemented passing screen and added delay to view shot before passing appears. Added header comment description for files missing it and updated authors for each file. Fat trim by removing commented out code and deleting placeholder assets. Game is good to go
33 | Aiden Patel | 2024-09-15 | 0 | 45 | copied work logs from Discord channel to excel spreadsheet
34 | Aiden Patel | 2024-09-15 | 0 | 35 | Created total time tracker at the bottom of the excel
35 | Aiden Patel | 2024-09-15 | 0 | 25 | reviewed requirements and added hit/miss alert after each shot to meet the requirement. Moved class structure file to documentation folder. Pushing everything now for hopefully the final commit
36 | John Newman | 2024-09-15 | 2 | 55 | Commenting, trimming, polishing toplevel: added comments for some reason ship.py: created new in_ship function to check for intersection as ishit doesn't work properly during ship placement (it would allow ships that had been checked once to intersect the second time), created get_direction function because its good practice to not access private attributes in other classes board.py: added some comments, removed row and column vars as they were unused in contructor, added type for shiplist in constructor battleship.py: added and corrected some comments, added typing to constructor for my peace of mind pygameloop: remove time import and time wait as pygame can do that, made pygame do waiting at win, added comments to all of the code, changed check-ship_v_ship to used in_ship instead of ishit for error correction, replaced some question comments, added suggestion comments for next project, beautified comments, fixed display artifacts and errors in ship placement section. Made more extensive documentation for game
|  | Total Time | Hours | Minutes
| Aiden Patel |  | 14 | 35
| Andrew McFerrin |  | 3 | 25
| John Newman |  | 13 | 56
| Kai Achen |  | 1 | 40
| Landon Pyko |  | 6 | 5